## Sheet1
Test cases
Case # | Case Description | Test steps | Test Data | Expected Result | Actual Result | Pass/Fail | Tester Name
1 | Check tower places correctly | 1: Select an affordable tower using card. 2: Left click tower ghost on placement zone. | Tower + multiple placement zones | Tower is placed and can begin shooting, currency is removed. | AE. | PASS | Luke Flegg | Once in editor. Once in build.
2 | Destroy an enemy with tower | 1: have a tower placed in the level. 2: allow an enemy to come into range of the tower. 3: allow tower to shoot enemy until they are destroyed. | Tower + enemy | Enemy hit has health reduced per shot until destroyed. | AE. | PASS | Luke Flegg
3 | Hit an enemy with a spell | 1: select an affordable spell using a card. 2: cast spell on enemy/group of enemies. | Spell + enemy/enemeies | All enemies in range are effected. | Spell aoE seems off at time, but mostly accurate. | PASS | Luke Flegg
4 | Lose all player health | 1: let 10 enemies pass through the level | Enemies | Loss event outputs a debug announcing loss. | AE.
5 | Finish all waves | 1: complete all waves in test level using towers, spells and standard gameplay without failing | towers, enemies, spells | Win event occurs, allowing return to menu. | AE.
6 | Swap cards | 1: Select an available card 2: with the card still selected, select another card by left clicking | 2 cards | currently selected card changes without using the previous card. | AE.
7 | Game builds and runs correctly | 1: In Unity, left click the file tab, click build and run | Game files, Unity | Game builds without errors. | AE.
8 | Levels load correctly | 1: launch the build, load each individual level once. | Game build | Level loads and begins without issue. | AE.
9 | Sprites load correctly | 1: In unity, run the editor build. 2: Load a level 3: See if sprites render | Towers, spells, levels | The level renders the sprites replacing the solid coloured squares. | Some sprites are too big or too small | FAIL | Ernestas Milinskas
10 | Sprites load after editing the sizes in the sprite editor | 1: In unity, run the editor build. 2: Load a level 3: See if sprites render | Towers, spells, levels | The level renders the sprites replacing the solid coloured squares. | AE. | PASS | Ernestas Milinskas
11 | Animations on the enemies | 1: In unity, run the editor build. 2: Load a level 3: See if the enemies are animated | Enemies | The animation plays while the enemy is moving | The enemies arent animated, instead its on of the frames from the animation | FAIL | Ernestas Milinskas
12 | Animations on enemies after implementing an animation controller on enemy scriptable object | 1: In unity, run the editor build. 2: Load a level 3: See if the enemies are animated | Enemies | The animation plays while the enemy is moving | AE. | PASS | Ernestas Milinskas
13 | Sprites act on the correct layer | 1: Load level 2, it will be the easiest to see any issues. 2: Place towers where enemy sprites would pass over or under. 3: Observe and ensure sprites behind a tower stay behind, and those in front are at the forefront. | Game build | No issues with overlapping sprites. | AE.
14 | Boss Spawns | 1: Load level 1 and play as normal until the final wave. 2: Ensure boss has spawned normally and fight them as normal | Game build | The boss should spawn, they're larger than other enemies and have high health. | AE.
15 | Menu in-game | 1: Load any level and let at least one enemy spawn 2: Pause the game using escape or the button in the top left | Game Build | The enemies should freeze in place when paused, then continue when unpaused. | AE.
16 | Menu leave level | 1: Load any level, let enemy spawn. 2: Open the menu with escape or upper left button. 3: Return to menu 4: Load a new level | Game Build | Enemies should freeze when paused, the menu should load and enemies should spawn/move in the new level . | AE.
17
AE. = As Expected